## Gap Worklog
HIPAA Compliance — Gap Analysis & Prioritized Worklog (Skilled Nursing Facility App)
Companion to HIPAA_Compliance_Reference.docx (requirements & citations) and Staff_Auth_Workflow.docx (staff auth flow diagram + Android/iOS/Web implementation pointers), both in the Compliance folder. This sheet tracks current-state gaps and fixes for product/dev to prioritize and action. Update Status and Owner as work proceeds.
ID | Category | Role / Area Affected | Current State | Gap / Risk | Recommended Fix | HIPAA / Standard Reference | Priority | Status | Owner | Created Date | Notes
1 | BAA / Vendor | Infrastructure (AWS) | Confirmed pending — AWS BAA has not yet been executed. | No signed BAA with AWS covers PHI processed via Cognito/S3. | Accept the AWS Business Associate Addendum in AWS Artifact for this workload's AWS account. | 45 CFR §164.308(b)(1); §164.314(a) | High | Not Started |  | 2026-07-16 | Precondition for everything else in this list. Confirmed pending as of 2026-07-20.
2 | BAA / Vendor | Infrastructure (AWS) | Cognito and S3 assumed HIPAA-eligible. | HIPAA-eligible services list changes over time and hasn't been re-checked against current architecture. | Cross-check every AWS service touching PHI (Cognito, S3, compute, logging) against AWS's current HIPAA-eligible services list. | 45 CFR §164.308(b)(1) | High | Not Started |  | 2026-07-16
3 | Encryption & Storage | PHI documents (S3) | Confirmed pending — SSE-KMS is not yet enabled on PHI document buckets. | Data may be sitting under default SSE-S3 (or unconfirmed encryption) rather than customer-managed KMS keys, weakening key-access auditability and Breach Notification safe-harbor protection. | Enable SSE-KMS with customer-managed keys on all PHI document buckets; deny non-HTTPS requests via bucket policy. | 45 CFR §164.312(a)(2)(iv) | High | Not Started |  | 2026-07-16 | Confirmed pending as of 2026-07-20. Call recordings tracked separately — see row 22. Also affects Breach Notification safe harbor (row 23).
4 | Encryption & Storage | All PHI traffic | TLS assumed in use for app traffic. | Not confirmed TLS is enforced (not just available) on every PHI-carrying endpoint, incl. PCC sync and internal service calls. | Audit all PHI-carrying endpoints (app↔backend, backend↔PCC, backend↔S3, internal service-to-service) to confirm TLS 1.2+ is mandatory with no plaintext fallback. | 45 CFR §164.312(e)(1)–(2) | Medium | Not Started |  | 2026-07-16
5 | Audit & Logging | All PHI access | Confirmed: the app has no structured audit controls today. | PHI record-level access (views, downloads, call playback, consent grants/revocations) is not logged at all — not just an infra-vs-app-level gap, there is currently no structured mechanism. | Design and add application-level audit logging for every PHI read/write, tamper-resistant, retained on a defined schedule. | 45 CFR §164.312(b) | High | Not Started |  | 2026-07-16 | Confirmed as of 2026-07-20 — no structured controls currently exist.
6 | Data Retention | Call recordings | No confirmed retention/deletion schedule for call recordings. | Indefinite retention of PHI-containing audio increases breach exposure without a documented purpose. | Define and enforce a retention/deletion schedule for call recordings; document rationale. | Minimum Necessary — 45 CFR §164.502(b) | Medium | Not Started |  | 2026-07-16 | See row 22 for the consolidated call-recording encryption + retention item.
7 | Data Integrity | PHI documents (S3) | Versioning status on PHI document buckets not confirmed. | Without versioning, accidental/malicious overwrites or deletions of PHI documents are not detectable or recoverable. | Enable S3 object versioning on all PHI/document buckets. | 45 CFR §164.312(c)(1) | Medium | Not Started |  | 2026-07-16
8 | Privacy Notice | Resident & family onboarding | No Notice of Privacy Practices step in onboarding. | Residents/family are not shown or asked to acknowledge the facility's NPP within the app. | Add an NPP link/acknowledgment step to resident and family onboarding flows; confirm correct NPP version per facility. | 45 CFR §164.520 | Low | Not Started |  | 2026-07-16 | Primarily the SNF's (covered entity's) obligation; app is a natural surface for it.
9 | Device Management | Staff mobile devices | No confirmed MDM policy referenced for staff devices. | Staff devices accessing PHI may lack remote wipe, lock-screen enforcement, or restrictions on local PHI storage. | Document and enforce an MDM policy for staff devices: remote wipe, lock-screen enforcement, no offline PHI cache. | 45 CFR §164.310(d) | Medium | Not Started |  | 2026-07-16 | Also a compensating control for the lost-device scenario (rows 10–11).
10 | Identity & Access | Staff & physicians | Lost/stolen device handled by staff calling facility admin to deactivate account in Cognito (global sign-out). | Cognito access tokens are stateless JWTs — AdminUserGlobalSignOut revokes refresh tokens but an already-issued access token keeps working (via local signature/expiry checks) until it naturally expires, unless the backend explicitly checks revocation status. | Enable Cognito token revocation (jti/origin_jti claims). Keep access token TTL short (5–15 min). Have the backend check a fast revocation lookup (keyed by jti, populated the moment global sign-out fires) on every PHI-serving request — don't rely on local JWT signature/expiry checks alone. | 45 CFR §164.312(a)(1)–(2) | High | Not Started |  | 2026-07-16 | This is the core fix; rows 11–12 are complementary, not substitutes.
11 | Identity & Access | Staff & physicians | Proposed: check account validity on app launch/foreground. | Only catches revocation at discrete launch/foreground events — a continuously open, foregrounded session between checks isn't covered. Only closes the gap if the check calls something that honors Cognito's revocation state (e.g., GetUser), not a local JWT re-validation. | Implement the launch/foreground check against a Cognito API call that enforces revocation (e.g., GetUser). Treat as a good addition on top of row 10's backend fix, not a replacement for it. | 45 CFR §164.312(a)(1)–(2) | Medium | Not Started |  | 2026-07-16
12 | Identity & Access | Staff & physicians | Proposed: push notification to trigger local token invalidation. | Push delivery isn't guaranteed or instant (network/OS constraints); doesn't help if the device is offline. | Use as a UX accelerant to shorten average time-to-lockout, layered on top of the server-side revocation check in row 10 — not a standalone control. | 45 CFR §164.312(a)(1)–(2) | Low | Not Started |  | 2026-07-16
13 | Identity & Access | Staff & physicians | No documented emergency access path if a clinician's MFA device is unavailable during a care emergency. | §164.312(a)(2)(ii) Emergency Access Procedure is a required (not addressable) specification and currently undefined for this app. | Define a break-glass access path (e.g., time-boxed elevated access granted by a second authorized staff member/admin), with mandatory post-hoc audit review of every use. | 45 CFR §164.312(a)(2)(ii) | High | Not Started |  | 2026-07-16
14 | Authentication | Staff & physicians | OTP delivery channel not confirmed (SMS vs. authenticator app/push). | If SMS-delivered, NIST 800-63B flags SMS as a “restricted” authenticator due to SIM-swap risk. | Confirm OTP delivery channel; offer TOTP app-based or push-based OTP as an alternative, at least for staff/physician accounts (broadest access). | NIST SP 800-63B (industry benchmark, not HIPAA text) | Medium | Not Started |  | 2026-07-16
15 | Identity & Access | External physicians | Physicians provisioned as app users; onboarding/offboarding process not confirmed. | Physicians aren't facility employees — no confirmed tie to medical-staff credentialing at enrollment, nor a defined deprovisioning trigger when their affiliation/privileges end. | Tie physician account creation to facility credentialing/medical-staff roster verification; define an offboarding trigger independent of employee HR offboarding. | 45 CFR §164.308(a)(3) (workforce/access authorization, by analogy) | High | Not Started |  | 2026-07-16 | Non-employee accounts are typically the weakest offboarding link.
16 | Audit & Logging | Staff & physicians | Lost-device deactivation handled manually by facility admin. | Not confirmed whether the deactivation event itself (who reported, when revoked) is captured in an audit trail. | Add an audit log entry type for account deactivation / global sign-out events, timestamped and tied to the reporting workflow. | 45 CFR §164.312(b) | Medium | Not Started |  | 2026-07-16 | Also feeds breach risk assessment if PHI exposure during the gap window is ever in question.
17 | Authentication | Family members & residents | Resolved design: no password, by intent, for adoption ease. Backend mediates login via Cognito Admin API; OTP is the primary factor. Mandatory biometric/PIN registration (Face ID > Fingerprint > Pattern > PIN) now serves as the intended second MFA factor. V1 ships this as a local-only biometric gate; V2 will add server-side verification. | OTP alone is single-factor; the biometric/PIN addition closes that as long as it's a real second factor. In V1 (local-only gate), the backend has no way to verify the biometric check actually happened — a modified client could skip it — so V1 does not yet provide server-verifiable two-factor assurance, even though the UI presents it as MFA. | V1 (in progress): ship the local biometric/PIN gate as designed. V2 (tracked separately): implement a device-bound key pair (Secure Enclave / Keystore, biometric-gated) with challenge-response signing verified server-side — e.g., via a Cognito CUSTOM_AUTH flow (DefineAuthChallenge / CreateAuthChallenge / VerifyAuthChallengeResponse Lambda triggers) — so the second factor is cryptographically enforceable, not just a local UI gate. | 45 CFR §164.312(d); NIST SP 800-63B AAL2 | High | In Progress |  | 2026-07-16 | V1/V2 split agreed 2026-07-29. Since the backend now calls Cognito Admin APIs directly, confirm that backend service runs under a tightly scoped, least-privilege IAM role.
18 | Consent & Family Access | Family members & residents | Resident signs a consent form on a staff iPad naming authorized family members; family member views the signed consent and acknowledges it via a checkbox on first login (no signature required from the family member). | Consent capture doesn't appear to distinguish who signed — the resident (self) vs. a personal representative acting under state-law authority. These are two distinct legal bases under HIPAA. | Add a field at consent capture: “Signed by: Resident (self) / Personal Representative — [authority type: POA / Guardian / Other]”. | 45 CFR §164.502(g); §164.510(b) | Medium | Not Started |  | 2026-07-16
19 | Consent & Family Access | Family members & residents | Consent appears to be set up via a staff-mediated iPad flow. | Not confirmed whether the resident/personal representative can revoke a family member's access directly and immediately from their own app, vs. only via another staff-mediated visit. | Confirm (or add) a self-service revoke-access control in the resident's app, enforced immediately across all of that family member's active sessions. | 45 CFR §164.510(b) | Medium | Not Started |  | 2026-07-16 | Real-time revocation was already flagged as a requirement in the reference document, Section 4.
20 | Session Management | All roles | Sessions currently auto-log-off after 7 days with no shorter inactivity lock in front of it. | No control today guards against an unattended, unlocked device between full logins — only the 7-day ceiling exists. | Ship the planned 5-minute inactivity lock. It must require genuine local re-authentication (PIN/biometric) to resume — a cosmetic screen dim that resumes on tap satisfies nothing. Use the same PIN/biometric mechanism for both staff and family/resident (also fixes row 17). | 45 CFR §164.312(a)(2)(iii) | High | In Progress |  | 2026-07-16 | Already on the team's roadmap (Next Steps #1).
21 | Session Management | All roles | Proposed change: 7-day auto-log-off only after 7 days of inactivity; mandatory full re-auth every 30 days even if continuously active. | Loosens today's absolute ceiling (currently 7 days regardless of activity) to 30 days for continuously active sessions — moves further from the NIST AAL2 benchmark (12-hour absolute reauthentication), which governs long-lived session/credential-compromise risk, a different risk than the unattended-device risk row 20 addresses. | Acceptable only as a documented risk trade-off, and only once row 20 (genuine 5-min local lock) and row 10 (server-side token revocation) are both in place. Otherwise, consider keeping the active-use ceiling closer to 7–14 days. Either way, write the rationale into the Security Risk Assessment explicitly. | NIST SP 800-63B AAL2 (industry benchmark, not HIPAA text) | Medium | Decision Needed |  | 2026-07-16 | Decision for product/security owner, not purely an engineering task.
22 | Encryption & Storage | Call recordings (PHI) | Call recordings are encrypted at rest, but the specific encryption method (SSE-S3 vs. customer-managed SSE-KMS) and a retention/deletion policy are both unconfirmed. | Without confirming encryption type, Breach Notification safe-harbor status (row 3's KMS rationale) can't be claimed for recordings specifically. Without a retention policy, PHI-containing audio may be retained indefinitely, increasing breach exposure with no documented purpose. | Confirm/upgrade call recordings to SSE-KMS with customer-managed keys (align with row 3). Separately, define and enforce a retention/deletion schedule specific to recordings, and document the rationale (e.g., tied to care-quality review windows, not indefinite). | 45 CFR §164.312(a)(2)(iv); Minimum Necessary — 45 CFR §164.502(b) | High | Not Started |  | 2026-07-20 | Consolidates the call-recording-specific parts of rows 3 and 6. Confirmed pending as of 2026-07-20.
23 | Breach Notification | Organization-wide | No incident response / breach notification runbook exists today. | §§164.400–414 require a documented risk assessment (the §164.402 four-factor test) to determine if an incident is a reportable breach, plus statutory notification deadlines (individuals: ≤60 days; HHS: ≤60 days for 500+ affected, annual log for under 500; media: required for 500+ in one state/jurisdiction). Without a runbook, there's no assigned owner for the risk assessment and a real risk of missing a deadline during an actual incident. | Draft an incident response runbook: assign who performs the breach risk assessment, define notification timelines and templates, and reference this app's specific systems by name (PCC sync, S3 buckets, Cognito, call-recording pipeline) rather than writing a generic policy. | 45 CFR §§164.400–414 | High | Not Started |  | 2026-07-20 | Confirmed not ready as of 2026-07-20. Should reference rows 3, 5, and 22 once those controls exist, since they affect safe-harbor and evidence available during an investigation.
24 | Data Integrity | Staff edits, family-submitted docs, physician-signed orders | Family members can edit their own information; the app accepts uploads of consent forms, mobile-scanned test reports, call recordings posted to PCC Communications, and physician-signed referral order summaries. Nothing is currently written back to PCC, but FHIR write-back APIs are available and planned soon. No marker currently distinguishes app-originated data/edits from PCC-synced data. | Once FHIR write-back is enabled, there will be no way to tell whether a given field or document is the authoritative PCC-sourced record or an app-originated edit/upload — risking silent overwrites, conflicting versions between systems, and attribution disputes. Family-editable fields also have no confirmed change-tracking (who changed what, when) today. | Needs dedicated analysis and design before FHIR write-back ships, covering at minimum: (1) a source/provenance marker (app-authored vs. PCC-synced) on every editable field and uploaded document; (2) change-tracking (versioning + audit trail) on all family-editable fields; (3) a conflict-resolution policy for the PCC write-back path (e.g., PCC remains system of record, app edits are proposed changes requiring PCC-side confirmation) defined before enabling FHIR writes. | 45 CFR §164.312(c)(1) | High | Needs Analysis |  | 2026-07-20 | Flagged as requiring analysis/solutioning, not yet a defined engineering fix. Blocks the planned FHIR write-back launch. Related to row 7 (S3 versioning), which is a narrower, already-actionable subset.
25 | Identity & Access | Staff & physicians | Biometric-gated app unlock relies on OS-level key invalidation (iOS biometryCurrentSet / Android's default biometric-enrollment invalidation) when device biometrics change, but app behavior on invalidation isn't yet defined. | Invalidating the local key alone doesn't stop misuse — if the app allows silently re-registering a new biometric right after invalidation, an imposter who enrolls their own biometric on a stolen/unlocked device can regain access without ever supplying the original password/OTP. | On catching the OS's specific 'key permanently invalidated' error (not a generic biometric-mismatch failure), wipe local session state, revoke the current Cognito session server-side (don't just redirect locally), and require a full password+OTP login before any new biometric can be enrolled. Log the invalidation event and, if feasible, alert the user via another channel (e.g., email) that a new biometric was registered on their device. | 45 CFR §164.312(a)(1)–(2); §164.312(d) | High | Not Started |  | 2026-07-29 | Confirm iOS uses biometryCurrentSet (not the similar-looking biometryAny, which does not invalidate) and Android does not disable setInvalidatedByBiometricEnrollment. Narrows one attack path; see row 26 for its limits.
26 | Identity & Access | Staff & physicians | Staff devices allow saved/autofilled passwords; OTP is delivered to the same device via SMS or an already-logged-in email app. | On a stolen but unlocked device, both authentication factors (autofilled password + device-delivered OTP) may be trivially available to whoever holds it — meaning the forced full re-login in row 25 does not fully protect against this specific scenario. The real backstop is prompt reporting and admin-side revocation. | No code fix alone closes this. Ensure the lost-device reporting process (facility admin deactivation) is fast and clearly communicated to staff, and prioritize row 10 (server-side token revocation), since that is the control that actually limits exposure once a device is reported lost. | 45 CFR §164.312(a)(1)–(2) | Medium | Not Started |  | 2026-07-29 | Documents a known limitation rather than a new fix — ties rows 10 and 25 together.
27 | Authentication | Staff & physicians | Temp password sent via both SMS and email at account creation. | Sending the identical secret over two channels doubles exposure (compromise of either channel exposes the credential) without a security benefit. | Send the temp password to only the channel the user will authenticate with; use the other channel solely for an out-of-band 'account created' notice. Confirm the temp password is single-use and expires quickly (e.g., 24–48 hours), not Cognito's longer default. | 45 CFR §164.312(d) | Medium | Not Started |  | 2026-07-29
28 | Authentication | Staff & physicians | Flow assumes a forced permanent-password reset happens after first login with the temp password (Cognito NEW_PASSWORD_REQUIRED), but this isn't explicitly documented or confirmed. | If unconfirmed, staff could continue using a system-generated temporary password indefinitely. | Explicitly document and confirm the forced password-reset step and the password complexity policy as part of first login. | 45 CFR §164.312(d) | Low | Not Started |  | 2026-07-29
29 | Authentication | Staff & physicians | The 5-minute inactivity lock unlocks via a tap plus biometric; Face ID could technically trigger passively without the tap. | A purely passive Face ID scan (no explicit user gesture) could be triggered by someone holding the device up to a distracted or non-consenting user's face. | Keep an explicit tap/gesture before triggering Face ID rather than a passive auto-trigger, and confirm the OS's attention/liveness detection is left enabled, not disabled for speed. | 45 CFR §164.312(d) | Low | Not Started |  | 2026-07-29
30 | Session Management | Staff & physicians | App-open/relaunch (after kill or reboot) shows a biometric lock screen. | If the underlying session/token has already expired or been revoked, showing a biometric lock screen first is a wasted, potentially misleading step — the app should route straight to full login in that case. | On every app launch, check session/token validity first (ideally a live check, not just a locally cached expiry) and branch: valid session → biometric lock screen; expired/revoked/fresh install → full password+OTP login screen directly. | 45 CFR §164.312(a)(2)(iii) | Medium | Not Started |  | 2026-07-29
31 | Device Management | Staff & physicians (Web/Desktop) | Plan assumes at least one OS biometric/PIN is registered on every device across Android, iOS, Mac, and Windows, or app usage is blocked entirely. | Reasonably safe for mobile (a lock-screen credential is nearly universal), but not safe for desktop web: many corporate/older Windows laptops lack Windows Hello hardware, and most Mac desktops (iMac, Mac mini, external-keyboard setups) have no Touch ID at all — macOS also lacks a broad OS-level PIN API equivalent to Windows Hello PIN. External physicians on personal, non-managed devices add a further access-denial risk with no obvious support path. | For web/desktop, don't rely on a biometric-hardware assumption (see row 32's web decision). Document a support path for external physicians who hit a hard block. Add a 'use password instead' escape hatch for temporary biometric failures (bandaged finger, PPE affecting Face ID, a faulty camera) rather than a hard lockout, given this is a clinical app where availability matters. | 45 CFR §164.312(d) | Medium | Not Started |  | 2026-07-29
32 | Session Management | Staff & physicians (Web) | Decision: implement the biometric-gated lock on mobile only for v1; web uses a simple full logoff after 15 minutes of inactivity (password + OTP to resume), with the same 7-day/30-day ceiling layered on top. | Reasonable v1 trade-off and compliant on its own terms, but web sessions often run on more physically shared/exposed workstations (nursing stations, shared office desktops) than a personal mobile device — 15 minutes may be looser than the actual physical risk warrants if any of these are shared/kiosk-style machines rather than personally-assigned laptops. | Confirm whether facility web access is via personally-assigned or shared workstations; tighten the timeout (e.g., closer to 5–10 min) for shared machines. Implement the check using elapsed wall-clock time since last activity (checked on tab/window focus or OS wake), not a live JavaScript countdown alone, since browsers throttle background timers and a naive implementation may not fire reliably after the machine sleeps or the tab is backgrounded. | 45 CFR §164.312(a)(2)(iii) | Medium | Decision Needed |  | 2026-07-29 | Revisit WebAuthn (Windows Hello / Touch ID via browser) in a later phase for parity with mobile and reduced login friction.
34 | Session Management | Residents & family members | Decision: 30-minute inactivity window for this role (vs. staff's 5 minutes), justified by a different risk profile — a personal device exposing at most one consented resident's data, not a shared workstation with broad multi-resident access. | None — this is a documented, risk-based decision, not an open gap. Recorded here so the rationale is captured for the Security Risk Assessment. | Implement the 30-minute window; document the staff-vs-resident risk-profile rationale explicitly alongside it. | 45 CFR §164.312(a)(2)(iii) | Medium | Not Started |  | 2026-07-29 | Decision made 2026-07-29.
35 | Session Management | Residents & family members | Plan: gate only sensitive content (health records, documents, consent management) behind the biometric/PIN check; allow low-sensitivity views (dashboard, messages, activity feed) to resume without re-prompting within the 30-minute window. | Reduces how often an elderly or low-tech user must authenticate at all, without weakening protection on the content that matters — but requires product to explicitly classify which screens count as "sensitive" vs. not, or the gating will be inconsistently applied. | Define and document the sensitivity classification per screen/feature; implement step-up authentication (biometric/PIN prompt) only when navigating into a classified-sensitive screen. | Minimum Necessary — 45 CFR §164.502(b) | High | Not Started |  | 2026-07-29 | Same pattern as mobile banking apps: view balance freely, authenticate to transact.
36 | Device Management | Residents (elderly-specific) | App mandates at least one biometric/PIN, else usage is prohibited entirely, with no accommodation defined for users who can't reliably manage any of them. | Elderly residents are more likely than staff or family to have unreliable fingerprint scans (thinner/drier skin), and some will have cognitive or vision impairment making even PIN entry difficult — a hard mandate risks locking residents out of their own health information with no recourse. | Confirm the PIN entry UI is accessibility-tuned (large touch targets, high contrast, forgiving of retries). For residents who genuinely cannot manage any device credential, define an explicit assisted-setup accommodation (a family member or facility staff helps set up/manage access) tied to the existing personal-representative concept, rather than a silent hard lockout. | 45 CFR §164.312(d); general reasonableness of Security Rule safeguards | High | Needs Analysis |  | 2026-07-29 | Needs a defined accommodation process, not just a UI fix — flagged as requiring analysis, matching row 24's convention.
37 | Identity & Access | Residents & family members | No lost-device reporting or revocation path is defined for this role. Unlike staff, there is no admin console or web access for them to use. | A lost or stolen resident/family device has no defined way to get access revoked promptly, unlike staff's "call facility admin" path. | Two complementary paths: (1) self-service — an in-app "manage my devices/sessions" screen, usable from any other device already logged into the same account, to revoke a specific session immediately; (2) staff-assisted — extend the existing staff app's resident/family management screen (already used for consent capture) with a "revoke this person's access" action, for cases with no second device to self-serve from (most relevant for residents specifically). Both should call the same backend session-revocation mechanism being built for staff (row 10), not a separate implementation. | 45 CFR §164.312(a)(1)–(2) | High | Not Started |  | 2026-07-29 | Staff-assisted path reuses the consent-management relationship already being built — avoids standing up a separate support channel.
38 | Identity & Access | Residents & family members | Same biometric-key-invalidation exposure as staff (rows 25–26) applies to this role once the mandatory biometric/PIN ships. | If the OS reports the biometric key as permanently invalidated (a new biometric was enrolled on the device) and the app allows silent re-registration, an imposter with a lost/found device could regain access without ever supplying the original OTP. | Apply the same fix as rows 25–26: on the OS's specific key-invalidated error, wipe local session state, revoke the session server-side, and require a full OTP login before allowing new biometric registration. Same iOS (biometryCurrentSet, not biometryAny) / Android (setInvalidatedByBiometricEnrollment) implementation guidance applies. | 45 CFR §164.312(a)(1)–(2); §164.312(d) | High | Not Started |  | 2026-07-29 | Mirrors rows 25–26 for this role.
39 | Session Management | Residents & family members | App relaunch (after kill or device reboot) shows the app lock screen. | Same issue as staff (row 30): if the underlying session/token has already expired or been revoked, showing the biometric lock screen first is a wasted, potentially misleading step. | Check session/token validity first (live check, not a cached expiry) and branch: valid session → lock screen; expired/revoked/fresh install → full OTP login directly. | 45 CFR §164.312(a)(2)(iii) | Medium | Not Started |  | 2026-07-29 | Mirrors row 30 for this role.
40 | Consent & Family Access | Residents & family members | The resident-signs / family-acknowledges (checkbox) consent flow (rows 18–19) was defined separately from this authentication flow, and the new sign-in write-up doesn't explicitly reference it. | Risk of the two designs drifting apart if not explicitly reconciled — e.g., unclear whether consent capture triggers the install-link SMS/email (sign-in step 1) and exactly when the checkbox acknowledgment happens relative to biometric registration (sign-in step 5). | Confirm and document explicitly how the consent/acknowledgment flow (rows 18–19) integrates with the sign-in sequence described here, so the two aren't maintained as separate, potentially inconsistent designs. | 45 CFR §164.502(g); §164.510(b) | Medium | Not Started |  | 2026-07-29 | Confirmation/documentation item, not a new technical gap.

## Legend
Column & Color Legend
Priority — High | Address before broader rollout / next release.
Priority — Medium | Address in near-term backlog.
Priority — Low | Good practice, lower urgency.
Status — Not Started | No work begun.
Status — In Progress | Actively being built (per team's stated roadmap).
Status — Decision Needed | Requires a product/security policy decision, not just engineering.
Status — Needs Analysis | Problem is confirmed but no defined fix yet — requires design/research before it becomes an engineering task.
Status — Done | Verified complete — update Notes with verification method/date.