## Read Me
IDT Reports — Ticket Review Sheet
For PM/Dev Lead/Architect review before anything is created in ClickUp.
Feature | IDT Reports v2 — SNF Care Coordination
Primary PRD | prd-idt-reports-v2.md (Ready for Development Lead & Architect review — Epic and Story creation)
SA source doc | feature-idt-reports-v2_SA-comments.md (review_round 4, Approved-with-changes — ready for Epics/Stories on everything except the Rehab Team authorization mechanism, which the Permissions epic depends on)
How this sheet is organized
This is a single combined ticket list on the "Tickets" tab, with a Layer column separating two sources that should not be blended (per this project's standing ticket-drafting rule):
• | SA Technical — pulled directly from feature-idt-reports-v2_SA-comments.md's "Recommended technical epics/stories/spikes" list, plus two small no-schema-impact items the SA doc flagged but never gave a dedicated epic line to (date-format standardization, status-filter removal) — carried over from idt-reports-handoff-round2.md and feature-idt-reports-v2_epics-stories-notes-round2.md so they aren't silently dropped.
• | Functional User Stories — drafted independently by the AI from the PRD's Scope (§2), Personas (§3), and Screen-specification (§5) sections. These are NOT sourced from the SA comments — that document explicitly covers only the technical side.
Open items / blockers carried into this sheet
BLOCKER — Archival semantics (PRD §11 item 1)
What "archived into the patient record" means — app-only, a push to PCC, or both — is unresolved; depends on confirming whether PCC's document APIs support updating/versioning an already-pushed document. Blocks archival stories only; flagged on the Spike row and should stay open until answered.
Medium priority — Director resident-assignment exemption (PRD §11 item 2, TD §11 item 20)
Resident-assignment gating is confirmed for Case Manager, Social Worker, and the Rehab Team. Whether the Director's facility-wide access is exempt from this same gating, or should also be scoped to assigned residents, was raised in design review and is not yet settled. SA round 4 notes the TD had previously carried this as an unstated assumption; it's now corrected to its real, still-open status. Flagged on the Permissions row and the Director oversight story.
Medium priority, ENGINEERING-ONLY, BLOCKS T17 — Rehab Team authorization mechanism (PRD §11 item 3, TD §11 item 21)
How the system determines which staff count as a Rehab Team member for authorization is deliberately left open. Per explicit PM direction (after consulting Engineering, which resolved the analogous signer-designation question via the staff object's mobile_access field), this one is reserved for Engineering to answer on its own — not to be decided by the PM, the AI, or the SA agent, even though a similar mechanism may end up applying. SA round 4 confirms the TD proposes no mechanism, and calls this out explicitly as a blocker for the Permissions epic (T17), not just a nice-to-have. Flagged on the Permissions row (T17) and the Rehab Team authorization row (T25).
Low priority — Date format: fixed vs. facility-configurable (PRD §11 item 4)
The mm/dd/yy date format is currently fixed product-wide. Raised for consideration, not yet decided: should it instead be a facility-configurable setting, the same pattern as staleDraftCleanupDays and versionRetentionYears? Flagged on the date-format standardization row (T26).
Revision — 6 new PM review comments applied
The PRD (prd-idt-reports-v2.md) and this sheet were both updated to reflect 6 new PM review comments: (1) Rehab Team authorization broadened from a single "Director of Rehab" designation to a facility-configurable designation list; (2) toggling a PT/OT discipline off now prompts a confirmation and clears its ratings on consent; (3) the Rehab mark-complete checkbox is now disabled once the report is Complete; (4) a new Encryption NFR requires all IDT report data (PCC-sourced and staff-entered) to be field-level encrypted; (5) the per-section Refresh controls are now a single report-level Refresh control; (6) "Chief Complaint" is renamed to "Diagnosis," confirmed available from PCC. New/updated rows on the Tickets tab are marked "UPDATED per PM review comment" or "NEW" in their Acceptance Criteria / Notes column for easy scanning — 4 new SA Technical rows were added (T24–T27) beyond the original 23.
Revision 2 — engineering consultation on signer/Rehab designations
After consulting Engineering: (1) eligibleSignerDesignations is dropped — no facility-configurable list is needed, since the staff object already has a mobile_access field valued "Doctor" for every signer-eligible user, and the signer-resolution query now reads that field directly (T6, T15, T21 updated; the Spike's item 1 is resolved). (2) The Rehab Team question is explicitly NOT resolved the same way — the PM directed that this be left as an open question for Engineering alone to decide, not the PM, the AI, or the SA agent, even though a similar existing-field approach may end up applying. It's moved from an engineering follow-up item into PRD §11 as Open Question item 3, and the corresponding Tickets row (T25) was rewritten to make clear no mechanism should be assumed or built yet.
Revision 3 — SA agent round 4 review, Approved-with-changes
The SA agent reviewed idt-reports-handoff-round3.md's 9 items against the TD (review_round 4, Approved-with-changes) and this sheet is updated to match. Eight of nine items are now fully resolved and TD-confirmed: Refresh consolidation matched the TD already (T2); Diagnosis rename (FS6) and signer-designation simplification (T6/T15/T21) are TD-confirmed; Rehab clear-on-deactivate (T22/FS11) is FULLY resolved — Sathish confirmed it clears ALL fields including Goal, and re-enabling starts fresh rather than restoring data; Rehab mark-complete-disabled (T23/FS12) is fully specified. Field-level encryption (T24/T1) is CONFIRMED BY SATHISH AS ARCHITECT, with a full TD §3.4a design (reusing the existing AES-256-GCM pattern) including the carry-forward decrypt/re-encrypt mechanism and no viable alternative to it. The SA agent also caught and resolved one inconsistency we hadn't flagged: PRD §4.1's weight-trend wording didn't match the TD's older calendar-week design for weightTrendSnapshot — confirmed by Sathish that the PRD wording is correct, and the TD is simplified to match (T19/FS6). Only two items remain genuinely open, both correctly left that way: the Rehab Team authorization mechanism (T25/T17 — now flagged as a blocker for the Permissions epic specifically) and the Director bypass question (T17). Date format (T26) remains open too, but low-priority and non-blocking. Ready for Epics/Stories on everything except the Rehab Team mechanism.
Note | This is a review artifact, not yet a ClickUp import. Titles/estimates/assignees are expected to be refined before ticket creation. Nothing will be created in ClickUp from this without a further explicit go-ahead.

## Tickets
# | Layer | Title | Description | Acceptance Criteria / Notes | Source
SA TECHNICAL — EPICS / STORIES / SPIKES (source: feature-idt-reports-v2_SA-comments.md)
T1 | SA Technical | Report data model & lifecycle | Design and implement the idtreports / idtReportVersions / idtReportDeletionLogs schema and the Draft→Complete status model with independently-cycling signature state. | createdByType/updatedByType are dropped from idtreports — confirmed remnants of the previous report structure, no replacement field needed. SA ROUND 4: encryption is now a confirmed dimension of this epic — see T24 for the full detail (TD §3.4a, closes former TD §11 item 24). Ready to scope on that dimension; build the three flagged implementation wrinkles (T24) as part of this epic, not as an afterthought. | SA comments §"Report data model & lifecycle"; TD §3.3, §3.4, §3.4a
T2 | SA Technical | Auto-populated data & Refresh | Create-time snapshotting of Patient Information, Weight Trend, and Active Medications, plus a Refresh endpoint/control that re-pulls current values into an open report without saving. | UPDATED per PM review comment: a single Refresh control on the open report refreshes all three auto-populated sections at once, replacing the earlier per-section (three-control) design. Available at any point in the report's life, including after signature; nothing persists until the user's next ordinary Save. SA ROUND 4 CONFIRMED: TD §3.3's Refresh design already matched this — one control across all three sections — so no TD change was needed; ready as-is. | TD §3.3, §6; PRD §4.1 (PM review comment; SA round 4 confirms match, no TD change)
T3 | SA Technical | Create & carry-forward, including bulk-create | Single- and multi-resident Create (bulk-create), Start blank, the Draft-only partial unique index enforcing "at most one open Draft per resident," and partial-failure toast handling. | Design-review item 13: add a "view details" affordance for the full skipped-resident list on bulk-create failures, beyond the toast's "+N more" truncation — frontend-only, the bulk-create endpoint already returns full per-item data. | TD §3.3, §3.6, §3.9
T4 | SA Technical | Bulk delete | Multi-select delete of Draft reports, re-verifying each report is still a Draft at delete time rather than trusting the client, with partial-failure toast handling. | Design-review item 13: same "view details" affordance recommended for bulk-delete's partial-failure toast — frontend-only, no new API needed. | TD §3.10
T5 | SA Technical | Discipline completion & rehab progression trend | Derived completion states (Pending/In-progress/Complete) for Case Manager, Social Worker, and Rehab Team columns; the report-over-report rehab progression trend table. | UPDATED per PM review comment: once the report's document status is Complete, the Rehab section's mark-complete checkbox becomes disabled/read-only (still shown ticked) — document status only moves forward and can't revert to Draft, so the checkbox has nothing left to control (see also T23 below for the standalone note). SA ROUND 4 CONFIRMED: fully specified in TD §3.4/§6, no open sub-questions — ready for story-writing as-is. | TD §3.3, §3.4, §6; PRD §5.3 (PM review comment; SA round 4 confirmed)
T6 | SA Technical | Send-for-signature & Sign | Signer-resolution query (attending MD + eligible PA/NP), single-select recipient picker, digital signature capture. | RESOLVED per engineering consultation and now formally confirmed by SA round 4: no facility-configurable designation list needed. The staff object's existing mobile_access field is valued "Doctor" for every signer-eligible user; the query reads this field directly instead of a new facility setting — documented in TD §3.3. This removes a facility setting, a rollout step, and a risk row the design previously carried (TD §3.7, §9, §10) — smaller scope for this epic than before, not larger. Ready for story-writing. | TD §3.3, §3.7, §9, §10; PRD §12 (resolved per engineering consultation; SA round 4 confirmed)
T7 | SA Technical | Staff mobile app notifications | Register "IDT report" as a third document type on the existing shared staff-mobile-app signature-notification workflow (already serving the Health Referral Order Summary and Medication List) — notify the chosen signer on Send for signature, and all staff in the resident's assignedStaff on Sign. | Needs the notification-type registration-mechanism confirmation from the Spike (item 2) before this reaches production. | TD §3.11
T8 | SA Technical | PDF, print, and fax | Re-template the existing PDF pipeline (buildIdtReportHtml, idtReport.pdf.service.ts) to the new schema; both existing endpoints (direct-download render, generate-and-store) carry forward unchanged. Also: drop the fax popover's saved-contacts shortlist for a single free-text number field with US phone format validation (client + server), and add a status field to faxLog. |  | TD §6, §3.4
T9 | SA Technical | Fax History section | Collapsed-by-default UI on the report summary rendering directly from the existing faxLog array (number/sent date-time/actor/status). No new endpoint needed — frontend-only once faxLog.status exists. | Exact status enum values depend on the fax-vendor Spike item. | TD §3.4, §6
T10 | SA Technical | List status display rework | Remove the per-row Status chip from both list tabs; add a Signature Status column (Not sent / Awaiting signature / Signed) to the Completed tab only, backed by the existing signature.state field. | No new index needed — backed by the existing signature.state field/index. | TD §6
T11 | SA Technical | Edited-after-signature indicator | Surface an indicator as the last item in the report form's sub-title, backed by the existing signature.editedAfterSignAt field — expose it (plus signature.state, per the design-review update) in the report-get response. | Wording: "Signed — edited after signature on [date]" (PRD §5.2/§6 rule 4/§7 rule 4). | TD §3.3, §3.4, §6
T12 | SA Technical | Grid sort/display fix | Three small, independent changes: (1) switch the list's default sort back to reportDate (from createdAt); (2) display Report Date on the Edit and Summary pages too, not just the list; (3) add the unsaved-changes confirmation dialog on navigating away from an unsaved report. | Design-review items 1, 2, 4. Item 3 is already committed in PRD §10 but was never previously captured in the TD; now documented with an explicit test case. | TD §6, §8
T13 | SA Technical | idtReportVersions schema fixes | Two independent fixes: (1) every version row must capture all three auto-populated snapshots (Patient Information, Weight trend, Active medications), not only team-entered content — a real bug caught, since a post-signature refresh would otherwise leave no record of what the auto data looked like at signing time; (2) add a residentId field to idtReportVersions, denormalized like facilityId, for direct resident-scoped audit queries. | Design-review items 11–12. | TD §3.4, §3.10
T14 | SA Technical | reportDate / createdAt sequencing fix | Decouple reportDate (display/filing only, moved by Refresh+Save) from createdAt (sole key for carry-forward ordering, the rehab progression trend, the general lookup index, and retention-cleanup anchoring). Detect "this save follows a Refresh" server-side by diffing incoming snapshot fields against what's persisted — no new client-supplied flag. | Confirmed by Sathish, ready for story creation. Update the four call sites, rename two indexes, add the Save-time diff, add the retention/ordering regression test (TD §8). Reference the TD directly — the PRD text alone only says reportDate moves and doesn't mention createdAt. | TD §3.3, §3.4, §3.6, §3.8
T15 | SA Technical | Facility-level settings & scheduled jobs | staleDraftCleanupDays, versionRetentionYears settings, plus the stale-draft and retention-cleanup scheduled jobs and their dry-run/safety rollout. | UPDATED per engineering consultation, confirmed by SA round 4: eligibleSignerDesignations is REMOVED from this list — no longer needed, since the signer query now reads the staff object's existing mobile_access field instead (see T6; TD §3.7, §9). Down from three settings to two. Do NOT add a rehabTeamDesignations setting either — the Rehab authorization mechanism is an open question reserved for Engineering (see T25); nothing should be built here until that's answered. Date format remains a separate, still-undecided possible third setting (T26, PRD §11 item 4, TD §11 item 22). | TD §3.7, §3.8, §9; PRD §12 (resolved/updated per engineering consultation; SA round 4 confirmed)
T16 | SA Technical | Data cleanup rollout | Verify-then-clear the pre-production idtreports collection before deploy — the existing collection holds only stale test records; no migration needed. |  | TD §9; PRD §6
T17 | SA Technical | Permissions | Server-side role-matrix enforcement per PRD §8, now including the resident-assignment check for Case Manager/Social Worker/Rehab Team (a resident must be in the caller's assignedStaff for Create/Edit/Complete) — reverses an earlier confirmed decision. | SA ROUND 4: NOT READY FOR STORY-WRITING on two distinct points. (1) OPEN QUESTION (PRD §11 item 2, TD §11 item 20, medium priority): do Directors keep their facility-wide bypass, or should they also be scoped to assigned residents? The TD previously carried the Director bypass as an unstated assumption; SA round 4 corrected this to reflect its real, still-open status rather than silently confirming it either way. (2) The resident-assignment requirement is now CONFIRMED to extend to the Rehab Team the same way it applies to Case Manager/Social Worker (no longer an open assumption) — but "Rehab Team" is no longer scoped to a single "Director of Rehab" designation, and HOW the system determines Rehab Team membership for this check is OPEN QUESTION (PRD §11 item 3, TD §11 item 21) — reserved for Engineering to decide; not the PM's, the AI's, or the SA agent's call, even by analogy to the now-resolved signer question. Do not build this part of the role-matrix check against an assumed field or list — see T25. | TD §6, §7; PRD §8, §11 items 2–3; TD §11 items 20–21 (SA round 4)
T18 | SA Technical | Case Manager / Social Worker list rendering | Multi-value column/filter UI update — a resident can have several Case Managers and Social Workers; the list resolves them live via a join (idtreports.residentId → residents.assignedStaff), the same pattern as the signer pool. | Flagged as a risk if missed before Epics/Stories are drafted — the PRD's list UI currently describes these as single-value columns and needs updating to render multiple names. | TD §10, §6
T19 | SA Technical | Resident weight-trend data (cross-feature dependency) | NOT part of the IDT Reports codebase — owned by whoever owns Resident Info/patient-record and the PCC integration layer. A new residentObservationTrends collection (one doc per residentId+type, fixed-size 3-reading ring buffer, no calendar-week bucketing), upserted by the same PCC webhook that writes to observations, consumed by both Resident Info UI (latest entry) and the IDT report (all 3, as its trend). | Fully designed and confirmed by Sathish (retention, encryption, recordedAt plaintext). Ready to scope once this upstream capability is built; IDT Reports is a downstream consumer only — track as a dependency for the Auto-populated data epic, not a ticket inside this feature's own list. NEW, SA ROUND 4 — independently discovered inconsistency, RESOLVED: PRD §4.1's report-level weight trend wording ("a rolling set of 3 readings ... no calendar-week grouping or bucketing") didn't match weightTrendSnapshot's former calendar-week-slot design in the TD, which predated this PRD wording. Confirmed by Sathish: the PRD wording is correct — weightTrendSnapshot is simplified to directly mirror residentObservationTrends.readings, with no calendar-week logic anywhere. Closes former TD §11 item 25. | TD §3.4; SA design-review item 7; SA round 4 (TD §11 item 25 closed)
T20 | SA Technical | Stale resident-data detection and remediation — FUTURE PHASE, DO NOT SCOPE NOW | Once the weight-trend capability above exists: a scheduled check for residents whose data hasn't refreshed in over a week — on-demand PCC pull first, then a staff notification via the existing mobile app workflow if still stale. | Tracked in TD §12 as a future-phase item, not something to scope now. Included here only so it isn't lost — do not create a build ticket for this yet. | TD §12
T21 | SA Technical | Spike — pre-implementation confirmations and coordination | One consolidated research/coordination task (not a build epic) covering external-confirmation items: (1) ~~eligible signer designation taxonomy~~ — RESOLVED, see T6; (2) notification-type registration mechanism; (3) Diagnosis (formerly Chief Complaint)/Code Status PCC-sync confirmation; (4) Referral workflow's tolerance of an anticipated, non-final discharge date; (5) archival/PCC-push semantics — BLOCKER, PRD §11 item 1; (6) fax vendor integration and send-status values; (7) Nurse-persona permission sanity check (expected no-op); (8) ~~IDT report encryption scope confirmation~~ — RESOLVED, see T24. | Nothing in this Spike blocks story creation for the core report. RESOLVED per engineering consultation, confirmed by SA round 4: item 1 no longer needs a discussion — the staff object's mobile_access field (valued "Doctor" for signer-eligible users) resolves it directly, see T6. Item 3's Diagnosis half is confirmed (renamed, PM confirms it's available in PCC, TD §3.4); Code Status's PCC-sync remains open. Item 5 gates only the archival stories. Item 6 gates only Fax History's exact status display. Item 7 gates nothing. Item 8, added and resolved this round: the field-level encryption scope in TD §3.4a (including the carry-forward decrypt/re-encrypt mechanism) is confirmed by Sathish as Architect — see T24; removed from this Spike's remaining scope. Owner: Architect/Development Lead, coordinating with the relevant external teams. NOTE: the analogous Rehab Team designation question is deliberately NOT part of this Spike, and not a quick-confirmation item — it's tracked separately as a blocker for the Permissions epic (PRD §11 item 3, TD §11 item 21), reserved for Engineering alone (see T17, T25). | SA comments §"Spike"; PRD §5.2, §11 item 3, §12; TD §11 items 21, 24 (SA round 4)
T22 | SA Technical | Rehab discipline toggle — confirm & clear ratings on deactivate | When a user turns a Rehab discipline toggle off (Physical Therapy or Occupational Therapy — the two disciplines with chip-rated fields) after ratings have been entered, prompt a confirmation that the discipline's ratings will be cleared. On confirm, clear that discipline's chip-rated assist-scale values (and, for Physical Therapy, the numeric Gait distance) and turn the toggle off. No confirmation is needed if nothing was entered. Does not apply to Speech Therapy, which has no rated fields to clear. | FULLY RESOLVED — SA ROUND 4: Sathish has now confirmed both previously-open sub-questions. (1) Clearing extends to ALL of the discipline's fields on deactivation, including the free-text Goal field, not only the chip ratings. (2) Re-enabling the toggle afterward STARTS FRESH — it does not restore the previously-cleared data. Fully specified in TD §3.4/§6, closes former TD §11 item 23. Ready for story-writing as-is. | PRD §5.2; TD §3.4, §6 (SA round 4 confirmed, TD §11 item 23 closed)
T23 | SA Technical | Disable Rehab mark-complete checkbox once report is Complete | Once the report's document status is Complete, the Rehab section's mark-complete checkbox becomes disabled/read-only (still shown ticked) — applies whether Complete was reached via an explicit tick + Submit, or implicitly via Submit alone. | Rationale: document status only moves forward and cannot revert to Draft (PRD §6 rule 2), so the checkbox has nothing left to control once Complete; it's informational only at that point. Small, well-scoped frontend change — no schema impact. SA ROUND 4 CONFIRMED: fully specified in TD §3.4/§6, no open sub-questions — ready for story-writing. | PRD §5.3, §6 rule 2; TD §3.4, §6 (SA round 4 confirmed)
T24 | SA Technical | IDT report data encryption (all fields) | All IDT report data — both PCC-sourced auto-populated snapshots (Patient Information, Weight trend, Active medications) and staff-entered content (Clinical Information, Rehab Status & Cognition, Discharge Planning, Orders/Discussion) — must be field-level encrypted at rest, consistent with how other PHI on the platform is handled. Applies to idtreports and idtReportVersions alike, not only to specific fields. | CONFIRMED BY SATHISH AS ARCHITECT — SA ROUND 4, closes former TD §11 item 24. Design: reuse the platform's existing per-field AES-256-GCM encryption approach, the same pattern already used for observations (TD §3.4a). Key implementation wrinkle, confirmed as unavoidable: carry-forward must DECRYPT the prior report's content and RE-ENCRYPT it fresh (new IV) onto the new report, rather than copying ciphertext directly. Sathish asked whether a better alternative exists — it doesn't: copying ciphertext as-is only defers the cost to the content's first edit and adds a fragile special-cased code path; deterministic encryption trades away semantic security; per-document data keys don't avoid the decrypt/re-encrypt step; referencing the source document instead of copying would reopen the idtReportVersions snapshot gap already fixed elsewhere in this design (T13). Full alternatives analysis in TD §3.4a. THREE IMPLEMENTATION WRINKLES TO BUILD CORRECTLY, not as afterthoughts: (1) carry-forward's decrypt/re-encrypt cycle; (2) the rehab-trend read-path's added decrypt cost; (3) the Refresh-diff (T14) must compare DECRYPTED values, not ciphertext. Ready to scope as part of T1 (Report data model & lifecycle). | PRD §9, §12; TD §3.4a (SA round 4 confirmed, TD §11 item 24 closed)
T25 | SA Technical | Rehab Team authorization mechanism — OPEN QUESTION, ENGINEERING ONLY | The Rehab Team is not limited to a single "Director of Rehab" designation — a facility's rehab team may include several designations (e.g. PT, OT, SLP, Director of Rehab). HOW the system determines Rehab Team membership for authorization (Create/Edit/Mark Complete on Rehab Status & Cognition, and the resident-assignment check in T17/§8) is not decided. | DO NOT DECIDE THIS — per explicit PM direction, following engineering consultation on the analogous signer-resolution question (T6/T21, now resolved via the staff object's mobile_access field). The PM was clear this Rehab question should be left open for Engineering to answer on its own, not settled by the PM, the AI, or the SA agent — do not assume a facility-configurable list, a specific field, or that the same mobile_access mechanism applies, even though a similar approach may end up being used. Tracked as PRD §11 item 3 (medium priority). SA ROUND 4 CONFIRMS: the TD proposes no mechanism for this (new TD §11 item 21) — correctly left open, not resolved by SA either, and explicitly called out as a BLOCKER for the Permissions epic (T17) specifically, not just a nice-to-have. The resident-assignment requirement itself IS confirmed to extend to the Rehab Team (no longer an open assumption) — only the membership-identification mechanism remains open. | PRD §8, §11 item 3; TD §11 item 21 (open question, engineering-only per PM direction; SA round 4 confirms it's a blocker for T17)
T26 | SA Technical | Standardize date format to mm/dd/yy everywhere | Replace the old split format (MMM D, YYYY on the report; MMM D in list columns) with a single mm/dd/yy format used everywhere a date renders (report, list, summary, PDF). Display-layer only. | No dedicated SA epic line — flagged as "no schema/design impact," but still needs its own implementation ticket per this project's ticket-drafting rule. No schema change; update the shared date-formatting utility/component product-wide. UNDER CONSIDERATION, NOT YET DECIDED (PRD §11 item 4, low priority): whether mm/dd/yy should instead be a facility-configurable setting (like staleDraftCleanupDays/versionRetentionYears) rather than a hard-coded value — if so, this ticket's scope grows to include a new facility setting and a per-facility default rollout step. Don't build the hard-coded version assuming it's final until this is settled. | PRD §4.3, §11 item 4; TD §11 item 22; idt-reports-handoff-round2.md item 3
T27 | SA Technical | Remove document-status filter from list Filters & Sort | Remove the status filter (All/Draft/Complete) from the list's Filters & Sort row — it was already a no-op inside a status tab, since the In-progress/Completed tabs already partition by status. | No dedicated SA epic line — flagged as "no schema/design impact," but still needs its own implementation ticket per this project's ticket-drafting rule. If the list query API accepts a status-filter parameter, drop or deprecate it. | PRD §5.1; idt-reports-handoff-round2.md item 4
FUNCTIONAL USER STORIES (drafted by AI from PRD §2 Scope / §3 Personas / §5 Screen specs)
FS1 | Functional Story | View and navigate the IDT Reports list | As a Clinical Staff member or Director, I want to see all IDT reports in one list, split into In-progress and Completed tabs, so I can find and open the report I need. | Two tabs, In-progress (default) and Completed, split by document status, not date. Columns: Resident, Report Date, Attending MD, Case Manager, Social Worker, Rehab Team. Completed tab only: Signature Status column. Discipline columns show Pending/In-progress/Complete; clicking a cell opens the report scrolled to that discipline's section, briefly highlighted. Neither tab has a date horizon — a draft stays In-progress indefinitely until completed or auto-cleaned after 15 idle days. | PRD §2.1, §5.1
FS2 | Functional Story | Search and filter the reports list | As a Clinical Staff member or Director, I want to search and filter the list, so I can narrow a large resident roster to the report I need. | Single full-width search field between tabs and filter row; matches resident name or room number within the selected tab, combining with filters. Filters: Attending MD, Case Manager, Social Worker, with a live result count; options built from reports actually present in the tab. No document-status filter (redundant with tabs). Sort: newest, oldest, resident A–Z, attending MD A–Z. Session-only, not persisted per user. | PRD §5.1
FS3 | Functional Story | Create a new IDT report (single or multiple residents) | As a Case Manager or Director, I want to create a new Draft report for one or more residents in a single action, so I don't have to repeat the flow per resident. | Single primary Create action opens a multi-select resident picker listing every current resident except those with an open Draft, alphabetically, filtering live as typed; no selection limit. Confirming generates a Draft per resident, pre-filled per §4.1/§4.2, and returns to a refreshed list. If one or more residents can no longer be created for, they're skipped and the rest of the batch still succeeds — a toast names the skipped resident(s) and why. | PRD §2.1, §5.1, §6 rule 5
FS4 | Functional Story | Delete a Draft report | As a Case Manager or Director, I want to delete a Draft report I no longer need, so stale or duplicate drafts don't clutter the list. | Delete is the only Actions-column control; enabled on Draft rows only, disabled with a hover reason on Complete rows. Confirmation modal names the report's date and resident, states only drafts can be deleted ("Keep report" / "Delete permanently"). Confirming performs a permanent hard delete and shows a toast. | PRD §5.1, §7
FS5 | Functional Story | Bulk-delete Draft reports | As a Case Manager or Director, I want to select multiple Draft reports and delete them in one action, so cleaning up several stale drafts doesn't take multiple round trips. | Each Draft row carries a select checkbox (Complete rows do not). Selecting rows surfaces a bulk action bar with count and a single "Delete selected" action. Confirmation modal states only drafts can be deleted ("Keep reports" / "Delete permanently"); confirming hard-deletes every selected report with a count toast. Reports that can no longer be deleted (e.g. completed by someone else) are skipped, named in the toast, and the rest of the batch still deletes. No bulk submit/send-for-signature — those stay single-report actions. | PRD §2.1, §2.2, §5.1
FS6 | Functional Story | View auto-populated clinical data on the report | As any Clinical Staff member opening a report, I want to see the resident's current patient information, active medications, and weight trend without re-entering them, so I don't have to manually compile them from PCC. | Patient Information: name, room, DOB, attending MD, admission date, **Diagnosis** (renamed from "Chief Complaint" per PM review comment; confirmed sourced from PCC — field renamed to patientInformationSnapshot.diagnosis in the TD, SA round 4 confirmed), diet, code status. Active Medications: name, dose, route, frequency, full active list as at report date, same order in the summary. Weight Trend: last 3 readings, most recent last, with direction of change; rolling set of 3, no calendar-week grouping — SA round 4 confirms weightTrendSnapshot now directly mirrors residentObservationTrends.readings with no calendar-week logic anywhere (an independently-discovered inconsistency, now resolved — see T19); N/A for missing slots or none on file; compacted to a single row. All marked "Auto from PCC," read-only, snapshotted at creation (not read live). | PRD §4.1, §5.2; TD §3.4 (SA round 4 confirmed)
FS7 | Functional Story | Refresh auto-populated data on an open report | As a Case Manager, I want to refresh the auto-populated sections on demand, so a report left open for a while doesn't show stale PCC data. | UPDATED per PM review comment: a single Refresh control on the open report (not one per section) re-pulls current values for all three auto-populated sections (Patient Information, Weight trend, Active medications) at once, replacing what's shown in each. Doesn't save by itself — refreshed values persist on the next ordinary Save. Available at any point in the report's life, including after signature. Saving after a Refresh moves the report date to that save date. SA round 4 confirms this already matched the TD's design — no build surprises expected here. | PRD §4.1 (PM review comment; SA round 4 confirmed match)
FS8 | Functional Story | Start a report from the previous report's carried-forward content | As a Case Manager, Social Worker, or Rehab Team member, I want a new report for a resident to pre-fill the team-entered content from their most recent report, so I'm not re-typing unchanged information. | Creating a report for a resident who already has one pre-fills all team-entered fields from the most recent report (any status, including a draft) and shows a banner naming its date. Auto-populated fields are always refreshed, never carried forward — banner states this. Carried-forward text is normal editable content, never diffed (except rehab progress, compared in the trend table). The Rehab mark-complete checkbox never carries forward — always starts unticked. | PRD §4.2
FS9 | Functional Story | Start a report blank instead of carrying forward | As a Case Manager, I want to discard carried-forward content in one action when the previous report doesn't apply, so I can start fresh without manually clearing every field. | "Start blank" clears every carried-forward field in one action and dismisses the banner. Cannot be undone; the previous report is unaffected. | PRD §4.2
FS10 | Functional Story | Record Clinical Information | As a Case Manager, I want to record the resident's change in condition and skin & wound status, so the team has an up-to-date clinical picture for the meeting. | Free-text "Change in condition since the previous report." Auto weight trend row shown in the same card. Skin & Wound Status as a free-text field within this same card (not its own section); wound measurements typed, not structured (structured documentation is next-phase). Field is optional — an empty Clinical Information section is a legitimate report. | PRD §3, §5.2, §5.3
FS11 | Functional Story | Complete Rehab Status & Cognition | As a member of the Rehab Team (PT, OT, or SLP), I want to record my discipline's assessment in the report, so the physician sees a complete rehab picture at signature time. | Prior Level of Function (free text) and Weight-Bearing Status (typeahead) head the section. PT block: active toggle, chip-rated assist scale for 5 tasks, numeric Gait distance, free-text Goal. OT block: assist scale for 3 tasks, free-text Goal. SLP block: single free-text Notes; Import Report button visible but inert/deferred this release. Cognition: one free-text field, no score/BIMS. No visit-frequency fields anywhere in this section. Section closes with its own mark-complete checkbox. UPDATED per PM review comment, FULLY RESOLVED per SA round 4: turning a PT or OT toggle off after ratings have been entered prompts a confirmation that those ratings will be cleared; confirming clears ALL of that discipline's fields — the chip-rated values, PT's numeric Gait distance, AND the free-text Goal field — and turns the toggle off; no confirmation needed if nothing was entered; doesn't apply to Speech Therapy (no rated fields). Re-enabling the toggle afterward STARTS FRESH — it does not restore the previously-cleared data. Both points that were previously open are now confirmed by Sathish. Separately, who counts as "Rehab Team" for this persona (not a single fixed "Director of Rehab" designation) remains an OPEN QUESTION reserved for Engineering to decide (PRD §11 item 3, TD §11 item 21) — not settled by the PM, the AI, or the SA agent; see the Permissions row. | PRD §3, §5.2, §8, §11 items 3; TD §3.4, §6, §11 item 21 (clear-on-deactivate confirmed by SA round 4; Rehab Team mechanism remains engineering-only)
FS12 | Functional Story | Mark the Rehab section complete | As a member of the Rehab Team, I want to explicitly mark my section complete when my assessment is done, so the list reflects my discipline's true status while the report is still a Draft. | Explicit checkbox in Rehab Status & Cognition. While Draft, the list's Rehab column reads Complete only when ticked (whatever the fields contain), In-progress otherwise. Submitting the report marks Rehab Complete regardless of the checkbox. If reopened after submission, the checkbox displays ticked by default. Never carries forward to a new report — always starts unticked. UPDATED per PM review comment: once the report's document status is Complete, the checkbox is disabled/read-only (still shown ticked) — document status can't revert to Draft, so the checkbox has nothing further to control at that point. SA round 4 confirms this is fully specified (TD §3.4/§6), ready for story-writing. | PRD §4.2, §5.3, §6 rule 2; TD §3.4, §6 (PM review comment; SA round 4 confirmed)
FS13 | Functional Story | Complete Discharge Planning | As a Social Worker, I want to record the resident's discharge plan, so the team has current discharge information at the meeting. | Fields: Destination, DME needed/owned, caregiver, planning notes. Optional — an empty section is a legitimate report. No completion control of its own; while Draft, reads Pending (nothing entered) or In-progress (anything entered); Complete only on submission. | PRD §3, §5.2, §5.3
FS14 | Functional Story | Record Orders/Discussion | As a Case Manager, I want to record care-continuation decisions and discharge-date-setting for the meeting, so the physician and team have a clear record of what was decided. | Decision chips "Continue Skilled Care" and "Discharge Date Set" (with its date); not mutually exclusive — both may be selected, stored and displayed as-is. Discharge date must be today or later (only strictly past dates rejected); represents an anticipated, not final, discharge. Setting it writes the date to the resident record (not just the report) so it's consumable elsewhere. Plus free-text orders and discussion notes. | PRD §5.2, §7
FS15 | Functional Story | See discipline completion at a glance on the list | As a Case Manager or Director, I want to see each discipline's completion status directly on the reports list, so I know who still needs to contribute without opening the report. | Each discipline column reads Pending, In-progress, or Complete; Pending drawn with a dashed border. Every cell is clickable and jumps to that discipline's section, briefly highlighted. A Complete report cannot show a Pending discipline — submission marks all three Complete. Nothing blocks Submit — an unticked checkbox or empty section doesn't prevent Complete and produces no warning. | PRD §5.1, §5.3
FS16 | Functional Story | Submit (mark Complete) a report | As a Case Manager or Director, I want to mark a report Complete once the meeting's content is recorded, so it moves out of Draft and into review, independent of the physician. | Submit marks Complete and opens the summary; confirmed in a dialog stating the consequence (editable afterward, won't go back to Draft). Does not involve the physician or send anything. Submitting an already-Complete report keeps it Complete and records the edit. Document status only moves forward — no un-complete. | PRD §5.4, §6
FS17 | Functional Story | Send a report for the physician's signature | As a Case Manager or Director, I want to send a Complete report to the attending physician or their PA/NP for signature, so the report gets a physician sign-off. | Enabled only once Complete; disabled with a tooltip beforehand. Picker lists the attending MD and their PA/NP, single-select — exactly one recipient even when more are listed. Records "Awaiting signature" with recipient and sent date. Re-sending replaces the pending entry and appends to submission history. Dispatches a push notification to the recipient identifying the document as an IDT report. | PRD §5.4, §6, §7
FS18 | Functional Story | Sign a report | As the Attending Physician or their PA/NP, I want to review the summary and sign it, so the report becomes part of the resident's signed record. | Signer signs the summary; report records Signed with signer and date. Signature doesn't change document status. Captured as a digital signature at the point of signing, as part of the Send-for-signature flow — not a credential step-up, not a third-party e-signature vendor. Dispatches a push notification to all staff assigned to the resident. No return-to-team or rejection flow — a report needing correction is edited and re-sent. | PRD §3, §5.4, §7
FS19 | Functional Story | Edit a report after it's been signed | As a Case Manager, Social Worker, or Rehab Team member, I want to correct a signed report when something needs fixing, so the record stays accurate without a separate addendum process. | A signed report can be reopened and edited any number of times; no addendum flow — an edit is just an edit, recorded with date/user in the audit trail. Report form's sub-title shows "Signed — edited after signature on [date]" once this happens — the only place surfaced; summary and list carry no stamp. Re-sending for a fresh signature is the team's judgment via the ordinary action. | PRD §5.2, §5.4, §6, §7
FS20 | Functional Story | View the rehab progression trend on the summary | As the Attending Physician (or reviewing staff), I want to see how each rehab measure has trended over the last few reports, so I can judge the resident's trajectory, not just this report's snapshot. | For each PT/OT chip-rated task, the summary renders a "2 Reports Ago / Last Report / This Report" trend table, populated in report sequence (not calendar time). Cognition and Speech Therapy are free text and not part of this table. Fewer than two prior reports → N/A in those columns. Read-only. | PRD §5.4
FS21 | Functional Story | Fax the report | As a Case Manager or Director, I want to fax the report as a PDF directly from the summary, so I can send it to a recipient who requires fax. | Available from the summary alongside Print; popover with a single free-text fax number field, validated to US phone format (10 digits, masked as typed) — no saved contacts. "Send fax" validates and confirms with a toast naming the number; "Cancel" dismisses. Available regardless of document/signature status; never changes either. Each send audit-logged (number, actor, timestamp). | PRD §5.4, §7
FS22 | Functional Story | View fax history for a report | As a Case Manager or Director, I want to see every fax sent for a report, so I can confirm what was sent and when. | Fax History section on the summary, collapsed by default; expands to list every fax sent — number, sent date/time, actor, send status. Sourced from the same audit log as the fax write; exact status values depend on the fax vendor integration (see Spike, Tickets row 21). | PRD §5.4, §12
FS23 | Functional Story | Export or print the report as a PDF | As any Clinical Staff member, Director, or Physician, I want to export or print the report as a PDF, so I have a portable, faithful copy of the record. | PDF reflects the full section layout: Patient Information, Clinical Information (incl. Skin & Wound), Rehab Status & Cognition (incl. PT/OT detail and the progression table), Discharge Planning, Orders/Discussion, Medications Details. Summary's Print button calls the generate-once-store-forever endpoint, not the browser's native print. A signed report renders faithfully with signer/date, no visual distinction for post-signature edits. | PRD §5.6
FS24 | Functional Story | See consistent empty-field display | As anyone reviewing a report summary, I want empty fields to display consistently, so I can tell at a glance what wasn't filled in versus what's missing data. | Any empty field — free text or structured — shows an em-dash “—” placeholder; unified across all field types; nothing left blank or omitted. | PRD §5.4
FS25 | Functional Story | Director oversight of all reports | As a Director/Administrator, I want to see every report and its status without authoring content, so I have facility-wide oversight of the IDT process. | Director sees all reports, their document status and signature state, and can delete drafts; does not sign. Can Create, Edit, and Mark Complete like Clinical Staff, per the permissions matrix. OPEN QUESTION (PRD §11 item 2, medium priority, NOT YET SETTLED): whether the Director's facility-wide access is exempt from the resident-assignment gating that now applies to Case Manager/Social Worker/Rehab Team. | PRD §3, §8, §11 item 2
FS26 | Functional Story | See the report date displayed consistently | As anyone viewing a report, I want the report date visible wherever I'm looking at the report, so I don't have to cross-reference the list to know when it was filed. | Report date is the creation date, not user-editable, except that saving after a Refresh moves it to that save date. Shown in the header of the report form and the summary, in addition to the list column (previously list-only). Fixed mm/dd/yy format everywhere a date renders. | PRD §4.3